## TO DO - By Key Dates
Use the box on the left to mark completed tasks. Use the columns on the right and the days to target deadlines. This version is for those who plan by a date countdown.
| Tasks | J | F | M | A | M | J | J | A | S | O | N | D
240 + days before fair
| Review application materials | X | [10 empty] | X
| Submit application | X | X | [7 empty] | X | X | X
Subscribe to email updates
120+ days before fair
| Start using Exhibitor Resources Library - www.maine.gov/dacf/bigeprep |  | X | X | X | X
| Orientation, review terms and conditions |  |  | X | X | X
| Submit logistic, staffing updates to Management |  |  |  |  | X
| Reserve lodging (e.g. hotel, rental, off-site RV, etc.) |  |  |  | X | X | X
80-90 days before fair (avg. June 1)
| RSVP for site visit (for 17-day renters paid in full) |  |  |  | X | X | X
| Reserve storage (off-site, dead) and amenities |  |  |  | X | X | X | X
| Current insurance certificates - Fair may view copies upon request |  |  |  | X | X | X
| Pay MDACF exhibit invoice – Due July 1 | [6 empty] | X
60-70 days before fair
| Use the box on the left to mark completed tasks. Use the columns on the right and the days to target deadlines. This version is for those who plan by a date countdown. Tasks: Provided final staffing headcount to Maine Building Management; Use the box on the left to mark completed tasks. Use the columns on the right and the days to target deadlines. This version is for those who plan by a date countdown. M: X; Use the box on the left to mark completed tasks. Use the columns on the right and the days to target deadlines. This version is for those who plan by a date countdown. J: X | - Complete necessary paperwork
| Site visit (only for 17-day renters paid in full) | [5 empty] | X | X
| Set up local banking (on-site or nearby) | [5 empty] | X | X | X
40-50 + days before fair
| Pay ESE for dead storage reservation | [5 empty] | X | X | X
| Completed paperwork required by ESE and/or town | [5 empty] | X | X | X
| Reserved internet | [5 empty] | X | X | X
| Use the box on the left to mark completed tasks. Use the columns on the right and the days to target deadlines. This version is for those who plan by a date countdown. Tasks: Reserved phone line (if needed—some Point of Sale systems require); Use the box on the left to mark completed tasks. Use the columns on the right and the days to target deadlines. This version is for those who plan by a date countdown. J: X; Use the box on the left to mark completed tasks. Use the columns on the right and the days to target deadlines. This version is for those who plan by a date countdown. J: X; Use the box on the left to mark completed tasks. Use the columns on the right and the days to target deadlines. This version is for those who plan by a date countdown. A: X | - Schedule event social media updates
40+ days before fair – FOOD and BEVERAGE exhibitors completed:
| Permit applications and payment to Town of W. Springfield |  |  |  |  | X | X | X
| Submit proof of training or certifications |  |  |  |  | X | X | X
| Allergen training (food) |  |  |  |  | X | X | X
| ServSafe training (food) |  |  |  |  | X | X | X
| TIPS (alcoholic beverage) |  |  |  |  | X | X | X
10 Days before fair (just before Labor Day)
| Review suggested packing list; finish packing |  |  |  | X |  |  |  | X
| Update emergency contact for self and staff |  |  |  | X |  |  |  | X
| Print a copies of important documents to keep on site |  |  |  | X
Second Friday after Labor Day - Fair begins (on site)
| Admission & parking passes –from Maine Building Management | [8 empty] | X
| Review emergency evacuation plan, designate a staff meet-up site | [8 empty] | X
| On-site inspection by town official; receive permits when pass | [8 empty] | X
| Set up exhibit and locate key areas | [8 empty] | X
Exhibition is over
| Clean up; remove all display materials, inventory, etc. | [8 empty] | X

## TO DO - By Category
Use the box on the left to mark completed tasks. Use the columns on the right to target deadlines. This version is for those who plan by topics or categories.
Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process
| Tasks | J | F | M | A | M | J | J | A | S | O | N | D
Paperwork, required info to Building Management or Fair
| Review application materials | X | [10 empty] | X
| Submit application | X | X | [8 empty] | X | X
| Subscribe to email updates | X | [7 empty] | X | X | X | X
| Reviewed Exhibitor Resources |  |  | X | X | X | X
| Orientation, review terms and conditions |  |  | X | X | X | X
| Submit logistic updates to Management | [5 empty] | X
| Current insurance certificates - Fair may view copies upon request |  |  | X | X | X | X
| Submitted final staffing headcount to Maine Building Management |  |  | X | X | X | X
| Requested, scheduled site visit (only for 17-day renters paid in full) |  |  | X | X | X | X
| RSVP for site visit (for 17-day renters paid in full) | [7 empty] | X
Expenses
| Reserve lodging (e.g. hotel, vacation rental, off-site RV, etc.) |  |  |  | X | X | X | X
| Reserve storage (off-site; on-site), and amenities |  |  |  | X | X | X | X
| Pay MDACF exhibit invoice – Due July 1 | [6 empty] | X
| Pay ESE for dead storage reservation | [5 empty] | X | X | X
| Admission credentials (for non complimentary) | [7 empty] | X | X
Permits, Licensing - Town of W. Springfield, Fair
| Obtain insurance certificates - Fair may view copies upon request |  |  |  | X | X | X
| Create online account (food permit application) |  |  |  | X | X | X
| Allergen training (food) | X | X | X | X | X | X
| ServSafe training (food) | X | X | X | X | X | X | X
| TIPS (alcoholic beverage) | X | X | X | X | X | X | X
| Liquor License Commission Meeting (alcoholic beverage) | [6 empty] | X | X | X
| On-site inspection by town official; receive permits when pass | [8 empty] | X
Promotion and publicity
| Contact collector for emails |  |  |  | X | X | X | X
| Professional marketing materials - product, price list, rack cards, signsetc. |  |  |  | X | X | X | X
| Scheduled event-related updates to social media and tag the Big E! fair |  |  |  |  | X |  |  | X | X
Sales, labor, inventory, revenue, admin, etc.
| Set up local bank account | [6 empty] | X | X | X
| Recruit staff |  |  | X | X | X | X | X | X | X
| Staff training | [6 empty] | X | X | X
| Inventory - ME PFG codes for Fair purchases due May 1 |  |  |  | X | X | X | X | X
| Set budget and sales goals |  |  |  | X | X | X | X
Event Preparation
| Start using Exhibitor Resources Library - www.maine.gov/dacf/bigeprep |  |  | X
| Review suggested packing list; finish packing |  |  |  | X |  |  |  | X | X
| Update emergency contact for self and staff |  |  |  | X |  |  |  | X | X
| Print a copies of important documents to keep on site |  |  |  | X | X | X | X | X
| Review emergency evacuation plan, designate a staff meet-up site | [8 empty] | X
| Set up exhibit and locate key areas | [8 empty] | X
Post-Event
| Clean exhibit space: remove all waste, tidy, ready for off-season deep clean | [8 empty] | X
| Remove all display materials, inventory, etc. | [8 empty] | X
Admission, Passes, Etc. (Limited Complimentary)
| Receive from Maine Bldg. Mgmt (at fair) | [8 empty] | X

## Blank Template
This version is for those who want to customize their own to-do list. Use the box on the left to mark completed tasks. Use the columns on the right to put an X under the month.
Color codes: Red = Due now! Yellow = Likely have a buffer if something goes wrong Green= OK to start process
| Tasks | J | F | M | A | M | J | J | A | S | O | N | D

## 2025 Fair Dates - Calendar
2025 Fair Dates
SUN. | MON. | TUES. | WED. | THURS. | FRI. | SAT.
KEY: |  | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13
Group A | Group D |  |  |  |  | ME
Group B | Group E
Group C
2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20
2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27
HNE
2025-09-28

## Load in- out table
Group | A | B | C | D | E | E
What Is The Exhibit Duration?
# of exhibit days | 17 | 6 | 6 | 5 | 1 | 1
Fair days | ALL ( # 1-17) | First six (#1 - 6) | Next six (# 7- 12) | Last five (# 13 - 17 ) | Maine Day | Harvest N.E.Day
Open to public | 10 AM - 9 PM | 10 AM - 9 PM | 10 AM - 9 PM | 10 AM - 9 PM | 10 AM - 5 PM | 10 AM - 5 PM
Exhibit days | Friday- Sunday | Friday-Wednesday | Thursday-Tuesday | Wednesday-Sunday | Saturday | Friday
Exhibit dates | 9/12-9/28/25 | 9/11-9/16/25 | 9/17-9/24/24 | 9/25-9/29/24 | 2024-09-14 | 2024-09-27
When Does Load in Start?
Time | 12:00 | 12:00 | ~ 9 PM until 10:30 PM | ~ 9 PM until 10:30 PM | 7:00 | 7:00
Day | Tuesday | Thursday | Wednesday night | Tuesday night | Saturday | Friday
Date(s) | 9/ | 2024-09-12 | 2024-09-18 | 2024-09-24 | 2024-09-14 | 2023-09-27
When Does Load in End?
Time(s) | 17:00 | 17:00 | 6:30 AM to 8:30 AM | 6:30 AM to 8:30 AM | 9:00 | 9:00
Day | Thursday eve | Thursday eve | Thursday morning | Wednesday morning | Saturday | Friday
Date(s) | 2024-09-12 | 2024-09-12 | 2024-09-24 | 2024-09-25 | 2024-09-14 | 2024-09-27
When Does Load Out Begin?
Time(s) | ~ 9 PM until 10:30 PM | ~ 9 PM until 10:30 PM | ~ 9 PM until 10:30 PM | ~ 9 PM until 10:30 PM | 17:00 | 17:00
Day | Sunday night | Wednesday night | Tuesday night | Sunday night | Saturday | Friday
Date(s) | 2024-09-30 | 2024-09-18 | 2024-09-25 | 2024-09-30 | 2024-09-14 | 2024-09-27
When Does Load Out End?
Time(s) | 6:30 AM to noon | 6:30 AM to 8:30 AM | 6:30 AM to 8:30 AM | 6:30 AM to noon | 19:00 | 19:00
Day | Monday | Thursday morning | Wednesday morning | Monday | Saturday | Friday
Date(s) | 2024-09-30 | 2024-09-19 | 2024-09-25 | 2024-09-30 | 2024-09-14 | 2024-09-27

## Sheet2 (hidden)
Group | # of exhibit days | Fair days | Must be open to public | Exhibit days | Exhibit dates | When Does Load in Start? | Load In Start | Day | Date(s) | When Does Load in End? | Load in End | Day | Date(s) | When Does Load Out Begin? | Load Out Start | Day | Date(s) | When Does Load Out End? | Load Out End | Day
A | 17 | ALL ( # 1-17) | 10 AM - 9 PM | Friday- Sunday | 9/12-9/28/25 |  | 12:00 | Tuesday | 9/ |  | 17:00 | Thursday eve | 2024-09-12 |  | ~ 9 PM until 10:30 PM | Sunday night | 2024-09-30 |  | 6:30 AM to noon | Monday
B | 6 | First six (#1 - 6) | 10 AM - 9 PM | Friday-Wednesday | 9/11-9/16/25 |  | 12:00 | Thursday | 2024-09-12 |  | 17:00 | Thursday eve | 2024-09-12 |  | ~ 9 PM until 10:30 PM | Wednesday night | 2024-09-18 |  | 6:30 AM to 8:30 AM | Thursday morning
C | 6 | Next six (# 7- 12) | 10 AM - 9 PM | Thursday-Tuesday | 9/17-9/24/24 |  | ~ 9 PM until 10:30 PM | Wednesday night | 2024-09-18 |  | 6:30 AM to 8:30 AM | Thursday morning | 2024-09-24 |  | ~ 9 PM until 10:30 PM | Tuesday night | 2024-09-25 |  | 6:30 AM to 8:30 AM | Wednesday morning
D | 5 | Last five (# 13 - 17 ) | 10 AM - 9 PM | Wednesday-Sunday | 9/25-9/29/24 |  | ~ 9 PM until 10:30 PM | Tuesday night | 2024-09-24 |  | 6:30 AM to 8:30 AM | Wednesday morning | 2024-09-25 |  | ~ 9 PM until 10:30 PM | Sunday night | 2024-09-30 |  | 6:30 AM to noon | Monday
E | 1 | Maine Day | 10 AM - 5 PM | Saturday | 2024-09-14 |  | 7:00 | Saturday | 2024-09-14 |  | 9:00 | Saturday | 2024-09-14 |  | 17:00 | Saturday | 2024-09-14 |  | 19:00 | Saturday
E | 1 | Harvest N.E.Day | 10 AM - 5 PM | Friday | 2024-09-27 |  | 7:00 | Friday | 2023-09-27 |  | 9:00 | Friday | 2024-09-27 |  | 17:00 | Friday | 2024-09-27 |  | 19:00 | Friday

## Sheet1 (hidden)
Group | Qty. days | Fair days | Exhibit days | Open to public | Load In |  |  |  | Load Out
A | 17 | ALL ( # 1-17) | Fri- Sun. | 10 AM - 9 PM | 12:00 | Tues. | 17:00 | Thurs. eve | ~ 9 PM until 10:30 PM | Sun. night | 6:30 AM to noon | Mon.
B | 6 | First six (#1 - 6) | Fri.- Wed | 10 AM - 9 PM | 12:00 | Thurs. | 17:00 | Thurs. eve | ~ 9 PM until 10:30 PM | Wed. night | 6:30 AM to 8:30 AM | Thurs. morn
C | 6 | Next six (#7- 12) | Thurs.- Tues. | 10 AM - 9 PM | ~ 9 PM until 10:30 PM | Wed. night | 6:30 AM to 8:30 AM | Thurs. morn | ~ 9 PM until 10:30 PM | Tues. night | 6:30 AM to 8:30 AM | Wed. morn
D | 5 | Last five (# 13 - 17 ) | Wed- Sun. | 10 AM - 9 PM | ~ 9 PM until 10:30 PM | Tues. night | 6:30 AM to 8:30 AM | Wed. morn | ~ 9 PM until 10:30 PM | Sun. night | 6:30 AM to noon | Mon.
E | 1 | Maine Day | Sat. | 10 AM - 5 PM | 7:00 | Sat. | 9:00 | Sat. | 17:00 | Sat. | 19:00 | Sat.
E | 1 | Harvest N.E. Day | Fri. | 10 AM - 5 PM | 7:00 | Fri. | 9:00 | Fri. | 17:00 | Fri. | 19:00 | Fri.

## Load in-out Calendar
2025 | SEPTEMBER |  | SUNDAY
CALENDAR YEAR | CALENDAR MONTH |  | FIRST DAY OF WEEK
45900 | 45901 | 45902 | 45903 | 45904 | 45905 | 45906
2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06
KEY: |  |  |  |  | Day 1 - First Day of Fair | Day 2
17- Day: Group A | Short Term: Group D | Group A (17-day) load In Times: 8:00AM -5:00 PM |  |  | [Group A - START
Short Term: Group B | Group E |  | 17 Day exhibitors: Building Mgmt distributes passes noon- 3PM at ME Building |  | [Group B - START
Short Term: Group C |  |  |  |  | Bldg open to exhibitors: 8AM-9:30PM | MAINE DAY
[ = start exhibit | ] = end exhibit |  |  |  |  | [Group E ]
Open to exhibitors: 8AM-9:30PM
Short term PM load out/in | Short Term AM load out/in |  |  | Short term PM load in @ noon
Group B |  |  |  | Group B load in noon- 5
Special event day
Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
Open to exhibitors: 8AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Open to exhibitors: 8AM-9:30PM
Group B - END]
|  |  | Group B - END] | [Group C START
|  |  | Short term PM load out/in | Short Term AM load out/in
Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16
Open to exhibitors: 8AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Building open to exhibitors: 9AM-9:30PM | Open to exhibitors: 8AM-9:30PM
|  | Group C- END] | [Group D - START
|  | Short term PM load out/in | Short Term AM load out/in |  | Harvest New England Day
Day 17 - Last Day of Fair |  | REMINDERS: | Maine Building hours of operation - Open to public 10AM-9PM
Open to exhibitors: 8AM-10:30PM | All remaining load out - Access: 6:30AM-12:00 (noon) PM | Deliveries to grounds and booth: between 8:00 and 9:15 AM Booth designee must be present at delivery. Alert management of delivery plans. Short term load in/out, unless told otherwise: LOAD IN: Evening before start date (after building closes to public), until 10:30 PM, and the morning of start date 7 to 9 AM. LOAD OUT: Evening of end date (after building closes to public), until 10:30 PM, and morning after 7 to 9 AM.
Group A END]
Group D END]
Updated Oct., 2023