## Sheet1
MOA Stipulation | Review Process | Completion Date
New Bridge Design Review Process MaineDOT will provide the SHPO, Bridge Design Committee, and the consulting parties, for their review and comments, details on aesthetic bridge design features, including public space, viewing, railing, and lighting options to ensure compatibility with existing historic features. | 30 calendar days to review information at 60% and 90% relevant design documents. | TBD
Historic American Engineering Recordation MaineDOT will provide recordation for the Frank J. Wood Bridge in accordance with HAER standards. Final document shall be distributed to Maine SHPO, Town of Brunswick, and Town of Topsham. | 45 calendar days for Maine SHPO to review and comment. Maine SHPO may request a second round of review. | Distributed by December 2020
National Register of Historic Places Nomination MaineDOT will prepare and submit to Maine SHPO a NRHP nomination for the Brunswick-Topsham Industrial Historic District. | The nomination will be developed in consultation with Maine SHPO. | Completed by December 2022
Outdoor Interpretive Panels MaineDOT will design and install 2 permanent outdoor interpretive panel displays (consisting of no more than 3 panels at each site) depicting the Frank J. Wood Bridge and earlier crossings, their history, and significance. The panels' content and materials will be prepared by MaineDOT and a 36 CFR 61 qualified architectural historian. | 45 calendar days for Maine SHPO, town officials, Pejepscot Historical Society, and consulting parties to review content, design, and location. | Draft panels will be distributed for review by December 2022. Panels will be installed by September 2023
MOA Stipulation | Review Process | Completion Date
Conservation of Existing Bridge Plaques MaineDOT will remove, store, and conserve 4 historic plaques on the Frank J. Wood Bridge. | Location of installation and plaque interpretation will be determined in consultation with FHWA, MaineDOT, Maine SHPO, town officials, and consulting parties. | Installed by September 2023
Adaptive Reuse or Reuse of Portions of the Structure Prior to dismantling, MaineDOT and FHWA shall offer the Frank J. Wood Bridge to any group that could legally take possession of the bridge and maintain it at a new location. | If no offers are received for adaptive reuse, then a portion and/or feature will be retained and offer to the town or the Pejepscot Historical Society. | No offers were received for adaptive reuse by deadline of May 17 (as published in the Times Record). Offers for portion and/or feature must be received by August 2019
Illustrated Booklet on History of the River Crossing MaineDOT will commission an illustrated booklet on the history of the river crossing, as well as document the complete story of the Frank J. Wood Bridge and its relationship to the community and the cultural landscape, including indigenous use in the area. The following will receive 10 printed copies: Maine SHPO, Town of Brunswick, Town of Topsham, Topsham Historical Society, Pejepscot Historical Society, Topsham Public Library, and Curtis Memorial Library. | 45 calendar days for Maine SHPO, Pejepscot Historical Society, and consulting parties to review and provide comment on 1 draft. | Distributed by September 2023
Indoor Traveling Exhibit MaineDOT will develop a single indoor traveling exhibit that share the story of the river crossing, including the Frank J. Wood Bridge. MaineDOT will be responsible for research, development, and design. MaineDOT will retain the services of a 36 CFR 61 qualified architectural historian to develop the exhibit. | 45 calendar days for Maine SHPO, Pejepscot Historical Society, and consulting parties to review draft content and design. | Distributed by September 2023